## sample
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8 | Week #9 | Week #10
Ashwini
What tasks did I work on / complete? | UI wireframes for user feedback and registration. | UI and DB setup. | Home screen with Google Maps API integration completed. | Search by location and vehicle completed. | Vehicle reservation, price calculation and feedback APIs developed. | Vehicle reservation and user feedback screens completed. | Timer to indicate reservation duration implemented. | Sanity testing and health check of overall application. | Researched ideal deployment configuration and resources. | Merged and integrated all modules with final round of testing.
What am I planning to work on next? | Starter code for UI and DB schema. | Home screen design and functionality. | Handling multiple search scenarios. | Setting up price and late fee calculation for reservation. | Feedback UI. | Reservation UI. | Testing and code refactoring. | Integration and demo prep.
What tasks are blocked waiting on another team member? | None - This was an independent task. | None - Google API was designed first and had no dependency | After getting backend APIs for search the integration was completed | None | None | None | None | None | None | Minor fixes but were quickly fix from both backend and frontend team
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Everyone's choice of UI framework was discussed. | Everyone's choice of server implementation was considered. | Unanimously agreed on technology stack |  | Discussed priority of deliverables. | Accomodated changes in UI with corresponding changes in APIs and DB. | Accomodated backend changes to appropriately reflect on the UI. | Balanced everyone's schedules to allow for streamlined development. | Addressed incorrect logic and corresponding fixes. | Successfully distributed workload among team.
Varsha
What tasks did I work on / complete? | UI wireframes for user feedback and registration. | UI and DB setup. | Home screen with Google Maps API integration completed. | Search by location and vehicle completed. | Vehicle reservation, price calculation and feedback APIs developed. | Vehicle reservation and user feedback screens completed. | Timer to indicate reservation duration implemented. | Sanity testing and health check of overall application. | Researched ideal deployment configuration and resources. | Merged and integrated all modules with final round of testing.
What am I planning to work on next? | Starter code for UI and DB schema. | Home screen design and functionality. | Handling multiple search scenarios. | Setting up price and late fee calculation for reservation. | Feedback UI. | Reservation UI. | Testing and code refactoring. | Integration and demo prep.
What tasks are blocked waiting on another team member? | None - This was an independent task. | None - Google API was designed first and had no dependency | After getting backend APIs for search the integration was completed | None | None | None | None | None | None | Minor fixes but were quickly fix from both backend and frontend team
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Everyone's choice of UI framework was discussed. | Everyone's choice of server implementation was considered. | Unanimously agreed on technology stack |  | Discussed priority of deliverables. | Accomodated changes in UI with corresponding changes in APIs and DB. | Accomodated backend changes to appropriately reflect on the UI. | Balanced everyone's schedules to allow for streamlined development. | Addressed incorrect logic and corresponding fixes. | Successfully distributed workload among team.
Belinda
What tasks did I work on / complete? | Completed - - Started work on - wireframes for Login/Sign Up Tool - mock flow. | Completed - Wireframe for login/Sign up Started work on - Wireframe for admin | Completed - Wireframes for admin/login/Sign Up Started work on - Login form Frontend . | Completed - Login Integration with backend Started work on - Implement frontend for Sign Up. Integrate Sign Up with backend. | Completed - Remaining integration work. Started work on - Vehicle listing/add/delete/edit. Feed back basic form done. | Completed - Integratiion of Vehicle edit, basic frontend completed. Feedback form integration completed. Started work on - Integrating add/delete | Completed - Integration of Vehicle add/edit/delete/list. Fronted completed for Vehicle type and vehicle List Started work on - Integrating vehicle type add/delete | Completed - Integration of Vehicle type add/edit/delete/list. Fronted completed for Vehicle type and vehicle List Started work on - Integrating vehicle type add/delete | Completed - Vehicle type intgration done Started work on -Members listing, terminate,update extend. Minor changes in other modules | Completed- Terminate,extend membership Started work on - testing - UI validations, integration test, edge cases
What am I planning to work on next? | Completing wireframs for admin | Implement frontend for login | Integrate Login with backend. Implement frontend for Sign Up | Vehicle listing/add/delete/edit, Implement feedback | Listing Vehicle type and identify a way to display prices. Work with Ashwini to integrate Feedback the reservation | Listing Vehicle type and identify a way to display prices. | Complete integration of vehicle add/delete | complete vehicle type integration. Members listing, terminate,update extend. | complete -Members listing, terminate,update extend. | ensure end to end works. Reduce as many bugs as possible
What tasks are blocked waiting on another team member? | None | Feedback for wireframes | Comments for the wireframes ( attributes etc). | None. | Backend routes for Vehicle add. Issues to be fixed for delete route. | figuring out a way to display prices, so that admin can edit/add etc | Vehicle type routes need to convert data to key value format | None | Terminate/ extend routes. Get Routes for extra feature addition
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Feedback - callout issues and sought feed back from other team members.
Kedar
What tasks did I work on / complete? | understand ZipCar backend on a high level | Planning/Designing on backend Api | Implementation of Search by location API | Testing of Search by Location with various test cases (extensive test) | Integration of search by with frontend | Implementation of Search by Vehicle | Implementation of Admin Functionality | Testing and Integration of Functionality with Frontend | Reservation | Reformating various Api based on changes
What am I planning to work on next? | Planning/Designing on backend Api | Implementation of Search by location API | Testing of Search by Location with various test cases (extensive test) | Integration of search by with frontend | Implementation of Search by Vehicle | Implementation of Admin Functionality | Testing and Integration of Functionality with Frontend | Reservation | Reformating various Api based on changes
What tasks are blocked waiting on another team member? | - | Frontend Requirements | - | Testcase Planning | - | Frontend Design to implement Search by Vehicle | Frontend Design and Admin DB | - | -
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Week #1: Feedback - gave costant feed and was open to suggestions